## CASSY-SDLC v0.01
Activity |  | Schedule
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Requirements Definition | Formulation of questionnaires | Schedule 2: 1 week
| Consultation/coordination with schools and offices | Schedule 2: 1 week
| Individual and focus group interviews | Schedule 3: 2 weeks
| Field observations | Schedule 4: 2 weeks
| Prototype generation | Schedule 5: 3 weeks
| Surveys and prototype demonstration | Schedule 6: 2 weeks
| Creation and maintenance of the SRS document | Schedule 8: 6 weeks
| Design of usability and acceptance tests | Schedule 21: 15 weeks
System & Software Design | Creation and maintenance of the design document | Schedule 11: 5 weeks
| Formulation of test cases | Schedule 21: 13 weeks
Implementation & Unit Testing | Development of main/host system and the plugin management subsystem | Schedule 16: 7 weeks
| Development of the task management subsystem | Schedule 21: 10 weeks
| Development of the class record subsystem | Schedule 17: 3 weeks
| Development of the administrator plugin | Schedule 18: 2 weeks
| Development of the class management subsystem | Schedule 21: 4 weeks
Integration and System Testing | Hardware compatibility tests | Schedule 23: 2 weeks
| Application of test cases/functionality tests | Schedule 23: 2 weeks
| Peer review (functionality, usability, and acceptance) | Schedule 24: 2 weeks
| User tests (functionality, usability, and acceptance) | Schedule 28: 5 weeks
| Summary and analysis of results | Schedule 29: 3 weeks
Operation & Maintenance | Deployment to volunteer target users | Schedule 29: 6 weeks
Evolution | bar: Schedule 6 to Schedule 7; Schedule 9 to Schedule 10; Schedule 23 to Schedule 30